## CALENDAR
CALENDAR
Date | Duration in days | Phases | Activity | % | Status | Fineshed | Peding | Completed
2026-06-12 | 10 | Phase 0 | Discovery & Requirements | 100% | Completed | 15.87% | 84.13% | In progress
2026-06-22 | 20 | Phase 1 | System Design & Architecture | 11.11% | In progress |  |  | Peding
2026-07-12 | 5 | Phase 2 | Project Setup | 0% | Peding
2026-07-17 | 25 | Phase 3 | Backend Development | 0% | Peding
2026-08-11 | 20 | Phase 4 | Frontend Development | 0% | Peding
2026-08-31 | 5 | Phase 5 | Testing & QA | 0% | Peding
2026-09-05 | 7 | Phase 6 | Deploy & Observability | 0% | Peding
Formulas:
Date = [Duration in days, row above]+[Date, row above]
2,4%

## Schedule
SPRING
Date | Phase | Task | Status
2026-07-01 | Discovery & Requirements | BRD — Business Requirements Document | 1
2026-07-02 | Discovery & Requirements | BRD — Business Requirements Document | 1
2026-07-03 | Discovery & Requirements | User Stories + Acceptance Criteria | 1
2026-07-04 | Discovery & Requirements | User Stories + Acceptance Criteria | 1
2026-07-05 | Discovery & Requirements | Priorização MoSCoW | 1
2026-07-06 | Discovery & Requirements | Relatorio Da Fase | 1
2026-07-07 | System Design & Architecture | High Level Design (HLD) | 1
2026-07-08 | System Design & Architecture | Diagramas de Caso de Uso | 0
2026-07-09 | System Design & Architecture | Diagramas de Classes e de Objecto | 0
2026-07-10 | System Design & Architecture | Database struturation | 0
2026-07-11 | System Design & Architecture | Database struturation | 0
2026-07-12 | System Design & Architecture | Interfaces dos Repositorios | 0
2026-07-13 | System Design & Architecture | API Design com OpenAPI/Swagger | 0
2026-07-14 | System Design & Architecture | ADRS | 0
2026-07-15 | System Design & Architecture | Relatorio Da Fase | 0
2026-07-16 | Project Setup | Estrutura das Pastas e Docker Compose e Migrações se possível | 0
2026-07-17 | Backend Development | Core Backend Development and Frontend | 0
2026-07-18 | Backend Development | Core Backend Development and Frontend | 0
2026-07-19 | Backend Development | Core Backend Development and Frontend | 0
2026-07-20 | Backend Development | Core Backend Development and Frontend | 0
2026-07-21 | Backend Development | Core Backend Development and Frontend | 0
2026-07-22 | Backend Development | Core Backend Development and Frontend | 0
2026-07-23 | Backend Development | Core Backend Development and Frontend | 0
2026-07-24 | Backend Development | Core Backend Development and Frontend | 0
2026-07-25 | Backend Development | Core Backend Development and Frontend | 0
2026-07-26 | Backend Development | Core Backend Development and Frontend | 0
2026-07-27 | Backend Development | Core Backend Development and Frontend | 0
2026-07-28 | Backend Development | Core Backend Development and Frontend | 0
2026-07-29 | Backend Development | Core Backend Development and Frontend | 0
2026-07-30 | Backend Development | Core Backend Development and Frontend | 0
2026-07-31 | Backend Development | Core Backend Development and Frontend | 0
2026-08-01 | Backend Development | Core Backend Development and Frontend | 0
2026-08-02 | Backend Development | Core Backend Development and Frontend | 0
2026-08-03 | Backend Development | Core Backend Development and Frontend | 0
2026-08-04 | Backend Development | Core Backend Development and Frontend | 0
2026-08-05 | Backend Development | Core Backend Development and Frontend | 0
2026-08-06 | Backend Development | Core Backend Development and Frontend | 0
2026-08-07 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-08 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-09 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-10 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-11 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-12 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-13 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-14 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-15 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-16 | Frontend Development | Core Backend Development and Frontend | 0
2026-08-17 | Testing & QA & Optmisation | Tests and Optmisation | 0
2026-08-18 | Testing & QA & Optmisation | Tests and Optmisation | 0
2026-08-19 | Testing & QA & Optmisation | Tests and Optmisation | 0
2026-08-20 | Testing & QA & Optmisation | Tests and Optmisation | 0
2026-08-21 | Testing & QA & Optmisation | Tests and Optmisation | 0
2026-08-22 | Testing & QA & Optmisation | Tests and Optmisation | 0
2026-08-23 | Testing & QA & Optmisation | Tests and Optmisation | 0
2026-08-24 | Testing & QA & Optmisation | Tests and Optmisation | 0
2026-08-25 | Testing & QA & Optmisation | Tests and Optmisation | 0
2026-08-26 | Deploy | Deploy on render | 0
2026-08-27 | Deploy | Fix Bug on render | 0
2026-08-28 | Deploy | Fix Bug on render | 0
2026-08-29 | Documentação | Create Handoff | 0
2026-08-30 | Documentação | Create Handoff | 0
2026-08-31 | Documentação | Publicação no linkedin e procurar clientes | 0

## Description
Centry Software-School Management Smart
Owner Name | Gabriel Pedro Aurélio
Owner Email | gabrielpedroaurelio@gmailcom
TimeLife | Two Months
Target School | High School Particular